Scrum

- Scrum Team Roles and Responsibilities

Role Allocation

Product Owner	 Wen Minxing	- Manage the Product Backlog

- Prioritize requirements

- Accept the increments completed in each Sprint

- Represent the interests of users and ensure the maximization of product value

Scrum Master	 Zhang Yeheng	- Ensure the correct execution of the Scrum process

- Help the team remove obstacles

- Facilitate team self-organization and continuous improvement

- Protect the team from external interference

Development Team

Zhang Yeheng	- Self-organize to achieve Sprint goals

Luo Shirui	- Cross-functional collaboration (back-end + front-end)

Zhang Chenjia	- Jointly commit to and deliver high-quality increments

Li Zhuolin	- Daily stand-up meetings to synchronize progress

2. Scrum Event Definitions

2.1 Sprint Cycle

Cycle Length: 2 weeks (4 Sprints in total, with a total cycle of 8 weeks)

Sprint numbers: Sprint 1 to Sprint 4

Sprint starts on Monday morning and ends on Friday afternoon (with review and retrospective).

2.2 Sprint Planning Meeting

Project	Explanation

Time	First day of each Sprint, 9:00 - 10:30 a.m. (1.5 hours)

Participants	All team members

Meeting Objective	Determine the work to be completed in this Sprint and set Sprint goals

Agenda	1. Product Owner presents the highest-priority requirements (30 minutes)

2. Team assesses workload and discusses technical solutions (30 minutes)

3. Team commits to Sprint goals and forms the Sprint backlog (30 minutes)

Output	Sprint backlog, clear Sprint goals

2.3 Daily Scrum

Project	Explanation

Time	Every working day, 9:00 - 9:15 a.m. (15 minutes)

Participants	All team members

Meeting Format	Stand-up meeting, focusing on three points

Three Questions	1. What was accomplished yesterday?

2. What is planned for today?

3. What obstacles need assistance?

Notes	- Do not delve into technical details

- Specialized discussions can be organized after the meeting

- Latecomers must explain the reason

2.4 Sprint Review

Project	Explanation

Time	Last day of each Sprint, 2:00 - 3:00 p.m. (1 hour)

Participants	All team members (external reviewers can be invited)

Meeting Objective	Demonstrate completed features and collect feedback

Agenda	1. Product Owner opens the meeting (5 minutes)

2. Team demonstrates completed features (30 minutes)

3. Discuss feedback and adjust the product backlog (20 minutes)

4. Confirm the achievement of Sprint goals (5 minutes)

Output	Updated product backlog, feedback records

2.5 Sprint Retrospective

Project	Explanation

Time	Last day of each Sprint, 3:15 - 3:45 p.m. (30 minutes)

Participants	All team members

Meeting Objective	Summarize improvements and continuously optimize the team's working methods

Agenda	1. Review the good aspects of the Sprint (10 minutes)

2. Analyze areas for improvement (10 minutes)

3. Formulate improvement plans for the next Sprint (10 minutes)

Discussion Framework	- Keep: What practices should be maintained?

- Problems: What difficulties were encountered?

- Try: What new methods can be tried in the next Sprint?

Output	Improvement plan list

3.Product Backlog

Definition: A prioritized list of all requirements, maintained by the Product Owner. It includes user stories, priorities, estimated workloads, acceptance criteria, etc.

Epic 1: Basic Framework Setup

P001 As a developer, I want to set up a Python development environment so that I can proceed with subsequent development. Highest 0.5 - Python 3.8+ installed successfully

- All dependent libraries installed successfully

- Project structure initialized. None Sprint 1

P002 As a developer, I want to load the ResNet50 pre-trained model so that I can perform image recognition. Highest 1 - Model can be successfully loaded

- Single test image can be inferred

- Inference time ≤ 5 seconds P001 Sprint 1

P003 As a user, I want the application to have a beautiful graphical interface so that I can operate it. High 2 - Window size 1100x700

- CustomTkinter theme unified

- Basic layout completed P001 Sprint 1

Epic 2: Data Preparation

P004 As a Product Owner, I want to organize the encyclopedic data of over 120 dog breeds so that I can provide complete information. Highest 3 - Number of dog breeds ≥ 120

- Each dog breed contains 11 fields

- Data format is JSON/Excel

- Data accuracy has been reviewed. None Sprint 1

P005 As a Product Owner, I want to organize the mapping table of Chinese and English aliases so that I can improve recognition accuracy. High 1 - Number of aliases ≥ 50

- Covering mainstream dog breed aliases

- Including common internet terms (such as "Erha") P004 Sprint 1

Epic 3: Image Selection and Preview

P006 As a user, I want to click a button to select a local image so that I can upload a dog photo. High 1 - Support jpg/png/bmp formats

- File selection dialog can be opened normally

- Display file path after selection P003 Sprint 2

P007 As a user, I want to see the preview of the selected image on the interface so that I can confirm the correct upload. High 1 - Image scaled to 500x400 area

- Maintain original aspect ratio

- Clear and visible P006 Sprint 2

P008 As a user, I want the recognition button to be available after selecting an image so that I can start recognition. Medium 0.5 - Button disabled when no image is selected

- Button becomes available after selecting an image

- Clear visual feedback P006 Sprint 2

Epic 4: Core of Dog Breed Recognition

P009 As a user, I want the system to analyze the image after clicking the recognition button so that I can obtain the recognition result. Highest 3 - Recognition starts after clicking

- Display "Recognizing" status prompt

- Automatically display result after recognition is completed

- Recognition time ≤ 5 seconds P002, P007 Sprint 2

P010 As a user, I want the system to be able to recognize common dog breeds so that I can understand the dog's breed. Highest 2 - Recognition accuracy of mainstream dog breeds ≥ 80%

- Recognition results can be mapped to local encyclopedias

- Support recognition of 120+ dog breeds P009 Sprint 2

P011 As a developer, I want to implement recognition result cleaning so that I can improve matching accuracy. Medium 1 - Remove content in parentheses

- Remove numbers

- Replace underscores with spaces P010 Sprint 2

Epic 5: Encyclopedia Information Display

P012 As a user, I want to view the name of the identified dog breed so that I can know what kind of dog it is. High 0.5 - Display the Chinese name of the dog breed on the interface

- Bold font to highlight

- Real-time update of the recognition result P010 Sprint 2

P013 As a user, I want to view detailed encyclopedic information about the dog breed so that I can have a comprehensive understanding. High 2 - Display 11 information fields

- Clear information layout

- Scrollable for long text P004, P012 Sprint 2

P014 As a user, I want to see a detailed introduction of the dog breed so that I can understand the breed's story. Medium 1 - Display the origin of the dog breed

- Display typical characteristics

- Text is easy to understand P013 Sprint 3

Epic 6: Enhanced Alias Mapping

P015 As a user, I want the system to recognize common aliases of dog breeds so that it is more in line with daily usage. High 2 - Input "Erha" to recognize as Husky

- Input "Jinmao" to recognize as Golden Retriever

- Alias matching success rate ≥ 90% P005, P010 Sprint 3

P016 As a user, I want the system to handle mixed Chinese and English input so that it is more flexible. Medium 1 - Support English breed names

- Support Chinese aliases

- Case insensitive P015 Sprint 3

Epic 7: Baidu Encyclopedia Backup Query

P017 As a user, I want to be able to query online when there is no local match so that I can obtain more information. Medium 2 - Automatically query when the network is normal

- Obtain a brief introduction from the encyclopedia

- Display the source of the query P010 Sprint 3

P018 As a user, I want a friendly prompt when the network query fails so that I know the reason. Low 1 - Timeout prompt

- No network prompt

- Parsing failure prompt P017 Sprint 3

P019 As a user, I want the query results to be integrated into the interface so that I can view them uniformly. Medium 1 - Unified format of encyclopedia information

- Mark "Baidu Encyclopedia" as the source

- Appropriate truncation of information length P017 Sprint 3

Epic 8: User Experience Optimization

P020 As a user, I want a loading animation during the recognition process so that I know it is being processed. Medium 1 - Display "Recognizing..." text

- Button state change

- Avoid interface freeze P009 Sprint 3

P021 As a user, I want error operation prompts so that I know how to operate correctly. Medium 1 - Warning when clicking recognize without selecting an image

- Prompt for incorrect image format

- Prompt for recognition failure P008 Sprint 3

P022 As a user, I want the interface to be aesthetically pleasing and unified so that I have a good user experience. Medium 2 - Comfortable color combination

- Appropriate font size

- Reasonable layout without being crowded P003 Sprint 3

Epic 9: Performance Optimization

P023 As a user, I want the recognition speed to be fast enough so that I don't have to wait for a long time. High 2 - Recognition time ≤ 5 seconds

- Optimize image preprocessing

- No significant lag P009 Sprint 4

P024 As a user, I want the application to not take up too much memory so that it can run on ordinary computers. Medium 1 - Memory usage ≤ 500MB

- Stable operation after model loading

- No memory leaks P002 Sprint 4

Epic 10: Completeness and Delivery P025 As a user, I hope the application can be packaged as an exe file so that it can be run by double-clicking. High 2 - Generate a single exe file

- No need to install the Python environment

- Can run on Win10/11 All Sprint 4

P026 As a user, I hope there is a user manual so that I can understand how to use it. Medium 1 - Include function introduction

- Include operation steps

- Include common problems All Sprint 4

P027 As a project team, I hope there are complete project documents for subsequent maintenance. High 1 - Scope statement

- Scrum process document

- Technical design document

- Test report All Sprint 4

4.2 Sprint Planning Details

Sprint 1 (Weeks 1-2) - Basic Framework and Data Preparation

Sprint Goal: Complete the construction of the project's basic framework and data preparation work.

Selected PBI	Sub-task	Responsible Person	Estimated Hours

P001	Install Python 3.8+ and dependent libraries	All	2h

P001	Initialise Git repository and project structure	Zhang Yeheng	1h

P002	Download ResNet50 pre-trained model	Zhang Yeheng	2h

P002	Compile model loading test code	Zhang Yeheng	3h

P003	CustomTkinter environment configuration	Li Zhuolin	2h

P003	Design main window layout	Li Zhuolin	4h

P004	Collect basic information of over 120 dog breeds	Wen Minxing	16h

P004	Organize into JSON format	Wen Minxing	4h

P005	Collect and organize alias mapping table	Wen Minxing	4h

-	Research on Baidu Baike API technology	Luo Shirui	4h

-	Design image preprocessing module	Zhang Chenjia	4h

Sprint 2 (Weeks 3-4) - Core recognition function

Sprint goal: Realize basic recognition function and complete a runnable prototype

Selected PBI	 Task Breakdown	 Responsible Person	 Estimated Hours

P006	 Implement file selection dialog box	 Li Zhuolin	 3h

P006	 Bind selection event	 Li Zhuolin	 2h

P007	 Implement image preview function	 Li Zhuolin	 4h

P008	 Implement button state linkage	 Li Zhuolin	 2h

P009	 Integrate recognition interface	 Zhang Yeheng	 6h

P009	 Implement recognition status prompt	 Li Zhuolin	 2h

P010	 Implement model inference logic	 Zhang Yeheng	 4h

P011	 Implement result cleaning function	 Zhang Yeheng	 3h

P012	 Implement dog breed name display	 Li Zhuolin	 2h

P013	 Implement encyclopedia data loading	 Wen Minxing	 4h

P013	 Implement information display control	 Li Zhuolin	 4h

-	 Optimize image preprocessing	 Zhang Chenjia	 6h

-	 Basic network request module	 Luo Shirui	 4h

Sprint 3 (Weeks 5-6) - Function Enhancement and Optimization

Sprint Goal: Enhance recognition capability and improve user experience

Selected PBI	Sub-task	Responsible Person	Estimated Hours

P014	Improve detailed description field	Wen Minxing	4h

P015	Implement alias mapping dictionary	Wen Minxing	2h

P015	Integrate alias matching logic	Zhang Yeheng	4h

P016	Implement Chinese-English fuzzy matching	Zhang Yeheng	3h

P017	Implement Baidu Baike search interface	Luo Shirui	6h

P017	Implement page parsing logic	Luo Shirui	4h

P018	Implement exception handling	Luo Shirui	3h

P019	Integrate encyclopedia results into interface	Li Zhuolin	3h

P020	Add loading animation effect	Li Zhuolin	3h

P021	Implement error prompt box	Li Zhuolin	2h

P022	Adjust interface aesthetics	Li Zhuolin	5h

-	Integration testing	All	4h

Sprint 4 (Weeks 7-8) - Complete Version and Delivery

Sprint Goal: Complete all functions and deliver the final product

Selected PBI	Sub-task	Responsible Person	Estimated Hours

P023	Identify speed optimization	Zhang Chenjia	6h

P023	Memory usage optimization	Zhang Chenjia	4h

P024	Performance testing and tuning	Zhang Chenjia	4h

P025	PyInstaller packaging configuration	Zhang Chenjia	4h

P025	Generate executable file	Zhang Chenjia	2h

P026	Compile user manual	Wen Minxing	6h

P027	Compile technical documentation	Zhang Yeheng	4h

P027	Compile test report	All	4h

-	Comprehensive functional testing	All	8h

-	Bug fixing	All	8h

-	Preparation for final presentation	All	4h

4. Team Work Specifications

4.1 Code Specifications

Python Code: Follow the PEP 8 specification

Naming conventions: Use lowercase with underscores for variable names, and camel case for class names.

Note: All key functions must have docstrings, and complex logic must have inline comments.

Version control: Use Git and follow the principle of "small steps, frequent commits"

4.2 Communication Norms

Instant Messaging: Establish a project WeChat group for daily communication.

Document Sharing: Leangoo Shared Project Documents

Code repository: Manage code using GitHub/Gitee

Issue tracking: Use Excel or online tools to record bugs and tasks.